# Worklog Version 3 Project Plan

Persistent task and performance feedback application

WORKLOG VERSION 3  |  MANAGEMENT REVIEW  |  27 OCTOBER 2026

Objective: deliver a database-backed application with administrator-managed user profiles, manager-owned task creation and feedback, employee task visibility and correction requests, and HR review of shared performance feedback. The application records human judgments and context; it does not calculate performance outcomes from task counts.

# Scope and decisions

| Decision | Proposed approach |
| --- | --- |
| Application foundation | Single-organization web application with Python standard-library server and persistent SQLite database for a controlled pilot. |
| Identity and access | Admin creates named profiles and assigns Employee, Manager, HR, or Admin roles. Server enforces each role and manager-to-employee reporting relationship. |
| Performance workflow | Manager records a 1–5 rating with narrative and optional task link, then explicitly shares it. HR records an independent grade, written review, and follow-up disposition. |
| Correction workflow | Employee requests correction with rationale; manager accepts or declines with a note. Manager edits task and feedback records; edits to shared feedback invalidate its HR review for reevaluation. |
| Deployment boundary | Development server binds to localhost by default. A production rollout needs HTTPS deployment, operational database/backups, retention policy, privacy/security review, and support. |

# Roles and accountable owners

| Role / owner | Responsibilities |
| --- | --- |
| Administrator | Create profiles, assign roles and managers, reset temporary passwords, deactivate accounts, inspect audit events. |
| Manager | Create work tasks for direct reports, edit/correct team tasks, rate and provide feedback, share feedback, resolve employee correction requests. |
| Employee | Review own tasks and shared feedback, update task status, request corrections to task or feedback records. |
| HR reviewer | Read shared feedback, record HR grade and written evaluation, mark reviewed or follow-up required. |
| Product / project owner | Approve definitions, workflow, pilot group, success criteria, and go/no-go decision. |
| Security/privacy and IT owners | Review identity, access, hosting, backups, retention, incident response, notices, and applicable organizational requirements. |

# 12-week roadmap

| Phase / schedule | Key activities | Deliverable and exit criteria |
| --- | --- | --- |
| 1. Discovery · Weeks 1–2 | Confirm rating rubric, task fields, roles, reporting relationships, sharing rules, HR grade meaning, correction handling, retention and policy requirements. Interview managers, employees, HR, and IT/security. | Approved scope, role matrix, data dictionary, rating guidance, correction policy, pilot measures and named owners. |
| 2. Architecture and controls · Weeks 2–3 | Confirm single-organization deployment, database location, account bootstrap, password/session policy, authorization checks, audit expectations, backup/restore and pilot hosting. | Approved architecture and threat review; documented operations and recovery approach. |
| 3. Backend and database · Weeks 3–5 | Implement SQLite schema, admin setup, profile lifecycle, role checks, team relationships, task API, password change/reset and audit events. | Persistent database and API supporting core role workflows; authorization scenarios accepted. |
| 4. Performance workflows · Weeks 5–7 | Implement manager ratings and narrative feedback, explicit share state, employee visibility, HR review/grade, linked performance task, correction requests and resolution history. | End-to-end manager → employee/HR workflow; HR review resets if shared manager feedback is corrected. |
| 5. Pilot preparation · Week 8 | Complete role-based acceptance walkthroughs, documentation, training, sample data, backup/restore rehearsal, privacy/security approvals and escalation route. | Pilot readiness decision; no unresolved critical access or data-loss issues. |
| 6. Pilot · Weeks 9–10 | Pilot with one team for two weeks. Review usability, feedback quality, correction handling, access, persistence, and employee understanding. | Pilot findings, measured success indicators, issues and go/no-go recommendation. |
| 7. Rollout and review · Weeks 11–12 | Train users, provision profiles, monitor adoption/support, review access and audit events, confirm operational backup and retention plan. | Approved rollout; 30-day review schedule and prioritized follow-up backlog. |

# Success measures

| Measure | Method / initial target |
| --- | --- |
| Manager usability | At least 80% of pilot managers can create a task and prepare the agreed feedback/review record in under five minutes per workflow. |
| Task freshness | Measure updates within 24 hours; an 80% initial target is subject to work-pattern and task-type interpretation. |
| Record quality | Sample task and feedback records with employees and managers; define a reconciliation method before setting an accuracy target. |
| Role access | All pilot scenarios pass server-side authorization checks; review denied access attempts and admin actions. |
| Employee understanding | Collect feedback on task visibility, rating rubric, shared feedback, HR review, and correction route. |
| Operational readiness | Complete a backup restore rehearsal and confirm named owners for retention, incident response, account recovery, and access review. |

# Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Task counts or manager rating treated as objective truth | Require written evidence and context; distinguish task completion, manager rating, and HR grade; keep final appraisal decisions with authorized people. |
| Misconfigured manager relationship exposes employee records | Server queries scope manager access to active direct reports; test reassignment and account deactivation scenarios. |
| Correction or changed feedback obscures history | Log changes and correction decisions; invalidate HR review when shared feedback is changed. |
| SQLite/local deployment is insufficient for broader rollout | Use as controlled pilot baseline only; review managed database, HTTPS, operational monitoring, backups, and scale requirements before expansion. |
| Unclear retention or legal obligations | Do not claim compliance; obtain organization-specific privacy, HR, and legal review before real-data use. |

# Next steps

Approve the rating scale, manager feedback sharing rules, HR grade purpose, and correction process.

Name project, HR, security/privacy, IT, and pilot owners.

Choose the pilot team and establish baseline success measures.

Confirm the hosting and database plan before any multi-user or non-local deployment.

Review pilot results and explicitly approve or defer rollout.